## Summary
Activity | Days | Start | End | Resource
Product Verification- Milestone 1 | 20 | 2017-11-22 | 2017-12-19 | Elias
Product Verification- Milestone 2 | 20 | 2018-02-15 | 2018-03-14 | Elias

## Activities
Verification Activities | Days | Resource
Device Operation | 5 | Elias
Device Configuration | 0 | Elias
Software Compatibility/LINC | 2 | Elias
Iridium transmission | 2 | Elias
Bluetooth connectivity? | 0 | Elias
Initial Unit Setup | 2 | Elias
GPS Logging and Accuracy | 2 | Elias
Temperature Test | 1 | Elias
Power/Battery/Rechargable battery | 2 | Elias
Flasher functionality | 2 | Elias
Device Performance | 1 | Elias
AIS functionality | 1 | Elias

## Time And Costing
Costs: | Item | Cost
| Modular Beacon To Test (Quantity 1) | TBD

## Version Information
Version: | 1
Document: | http://dev.metoceandata.local:8080/svn/Product_Verification/Project Management/KUM/Modular_Beacon_Verification_Schedule.xlsx